## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Norzagaray Water District Procurement Monitoring Report as of December 31, 2021
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Purchase of Motorcycle unit | [19 empty] | Engineering | No | Shopping | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 05/26/2021 | N/A | N/A | N/A | COMPLETED | 2021 | Corporate Budget | 95000 |  | 95000 | 93625 |  | 93625 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Consultancy for ISO | [19 empty] | All Division | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 08/23/2021 | 08/24/2021 | 08/27/2021 | 2021-01-09 | COMPLETED | 2021 | Corporate Budget | 200000 | 200000 |  | 200000 | 200000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Application for New Connection of Electrical Services in Villarama | [19 empty] | Engineering | No | Direct Contracting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 06/22/2021 | 06/23/2021 | 06/29/2021 | 06/30/2021 | COMPLETED | 2021 | Corporate Budget | 600000 |  | 600000 | 373355 |  | 373355 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Purchase of 2 sets of Read & Bill device with printer | [19 empty] | Commercial | No | Shopping | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/22/2021 | N/A | N/A | N/A | COMPLETED | 2021 | Corporate Budget | 210000 |  | 210000 | 208500 |  | 208500 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [40 empty] | 11520000
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 4360212.4
Total Savings (Total Alloted Budget - Total Contract Price) | [40 empty] | 1686847.84
0N-GOING PROCUREMENT ACTIVITIES
| Supply, Delivery, Installation and Commissioning of Two (2) 40 HP Horizontally Installed Submersible Booster Pump and Motor and Corresponding Fittings and Materials at Norzagaray Heights Resettlement | [19 empty] | Engineering | No | Public Bidding | 2021-08-01 | 2021-04-03 | 03/19/2021 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-07-04 | 2021-12-04 | 04/22/2021 | 05/20/2021 | 10/20/2021 | On-going project | 2021 | Grant | 3310000 |  | 3310000 | 3276900 |  | 3276900 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Procurement of HDPE Tubing and Plastic Fittings | [19 empty] | Engineering | No | Public Bidding | 03/15/2021 | 2021-08-04 | 04/20/2021 | 2020-03-17 | 2020-04-06 | 2020-04-06 | 2020-06-05 | 2021-10-05 | 05/21/2021 | 2021-01-06 | 2021-03-06 | Staggered Delivery | 2021 | Corporate Budget | 1420000 |  | 1420000 | 1419604 |  | 1419604 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF GI, DI & BRASS FITTINGS FOR CY 2022 | [19 empty] | Engineering | Yes | Public Bidding | 10/29/2021 | 11/16/2021 | 11/23/2021 | 2021-06-12 | 2021-06-12 | 2021-06-12 | 2022-04-01 | 2022-11-01 | 2022-12-01 | On-going process | On-going process | On-going process | 2022 | Corporate Budget | 1920000 |  | 1920000 | 1661285 |  | 1661285 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF WATER METER FOR CY 2022 | [19 empty] | Engineering | Yes | Public Bidding | 10/29/2021 | 11/16/2021 | 11/23/2021 | 2021-06-12 | 2021-06-12 | 2021-06-12 | 2022-04-01 | 2022-11-01 | 2022-12-01 | On-going process | On-going process | On-going process | 2022 | Corporate Budget | 2550000 |  | 2550000 | 2544000 |  | 2544000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF UNPLASTICIZED POLYVINYL CHLORIDE (UPVC) PIPE 4”, 6” AND 8” DIAMETER | [19 empty] | Engineering | Yes | Public Bidding | 10/29/2021 | 11/17/2021 | 11/24/2021 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2022-06-01 | 2022-11-01 | 2022-12-01 | On-going process | On-going process | On-going process | 2022 | Corporate Budget | 1215000 |  | 1215000 | 1055221 |  | 1055221 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Procurement of Construction of Norzagaray Water Supply Improvement Project | [19 empty] | Engineering | Yes | Public Bidding | 12/13/2021 | 12/15/2021 | 2022-05-01 | Public Bidding on February 2, 2022 | [7 empty] | On-going process | On-going process | ADB | 44600 |  | 44600 | N/A | N/A | N/A | COA/PICE | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [39 empty] | 10459600
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | Foztin Joy T. Palad | [10 empty] | Lazaro B. Pascual | [10 empty] | Engr. Aimer B. Cruz
[21 empty] | BAC Member | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity